## Sheet1
PROJECT REPORT - WORK DISTRIBUTION
Project Name | Algorithmic forex trading and back testing system |  | Reporting Period | 1/3/2025 - 22/3/2025
Project Manager | Lê Minh Nguyên |  | Project Due Date | 2025-03-22
Compiled By | Lê Minh Nguyên |  | Date Submitted | 2025-03-22
SUMMARY
Student ID | Full Name | Contribution
K224161815 | Lê Văn Hiếu | 100%
K224161822 | Nguyễn Thị Yến Kiều | 100%
K224161829 | Lê Minh Nguyên | 100%
K224164830 | Đặng Anh Như | 100%
K224161839 | Nguyễn Chí Khánh Trình | 100%
TASKS
Task | Details | Deadline | Member | Note
BUILDING APPLICATION
Collect Data | Collect data for model training | 2025-03-05 | Đặng Anh Như
Designing UI - PyQt6 | Building user interface using PyQT6 Framework | 2025-03-06 | Nguyễn Thị Yến Kiều
Coding Backend | Coding backend that connect UI to other functions | 2025-03-06 | Lê Minh Nguyên
Build Database | Building MongoDB database and process, importing data | 2025-03-07 | Lê Minh Nguyên
Training LSTM | Training LSTM model for price prediction | 2025-03-10 | Đặng Anh Như
Coding Trend Following Model | Coding Trend Following Trading Model and back testing system | 2025-03-10 | Lê Minh Nguyên
Compiling Codebase | Combine all code file from members to make a complete app | 2025-03-12 | Lê Minh Nguyên
WRITING REPORT
Chapter 1: Project Overview |  | 2025-03-10 | Lê Văn Hiếu
Chapter 2: Theoretical Background |  | 2025-03-10 | Nguyễn Trí Khánh Trình
Chapter 3: Researching Situation |  | 2025-03-12 | Lê Văn Hiếu
Chapter 4: Proposed Model |  | 2025-03-15 | Đặng Anh Như
Chapter 5: Intergration & Deployment |  | 2025-03-15 | Nguyễn Thị Yến Kiều
Chapter 6: Evaluation, Recommendation, and Conclusion |  | 2025-03-15 | Nguyễn Trí Khánh Trình
Work Distribution Sheet |  | 2025-03-21 | Lê Minh Nguyên
Demo Video |  | 2025-03-22 | Lê Minh Nguyên
Presentation Slide |  | 2025-03-22 | Nguyễn Thị Yến Kiều